## Slide 1
GUJARAT POLICE HACKATHON / TEAM PLAN
One platform.
Evidence-led alerts.
A practical hybrid CCTV architecture
Scope • implementation • ownership • safeguards
Proposed approach | 31 August 2026
Notes: Our goal is a working, defensible vehicle-watchlist system using authorised feeds. We are proposing the implementation, not claiming an existing production platform. This team deck explains the choices and execution plan; detailed implementation guidance is included in the notes.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 2
TEAM PROPOSAL
Build around the evaluation test
The brief rewards a complete working chain before optional innovation.
GUJARAT CCTV / Proposed design • targets are not measured results
02
Mandatory demonstration
Onboard approximately 50 heterogeneous cameras and process the supplied feeds.
Find the designated registration number; show timestamped sightings and GIS history.
Continuously match a representative watchlist and generate reviewable alerts.
Evidence for the judges
Working backend, own-feed video, government-feed video, and output report.
Architecture, security, interoperability, and a credible path to 80,000 cameras.
Bonus features do not compensate for missing mandatory requirements.
Notes: The supplied brief describes qualitative evaluation; do not invent scoring percentages. Prioritise successful test case, working platform, analytics quality, architecture, scalability and complete submission. Clarify whether all approximately 50 feeds must run simultaneously, the vehicle passage schedule, and the permitted hosting environment. A polished interface with replayed alerts is not sufficient.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 3
TEAM PROPOSAL
Choose a phased hybrid
Model 1 is a shared foundation, not a complete operational alternative.
GUJARAT CCTV / Proposed design • targets are not measured results
03
Model | Role in our solution | Main trade-off
1 • Registry + GIS | Always included; inventory and ownership | Inventory alone cannot detect vehicles
2 • Direct integration | First working feed-to-alert path | Network access and source load
3 • VMS federation | Add supported adapters incrementally | Vendor API, SDK and licence dependence
4 • Central VMS | Selective incident evidence only | Full central recording is costly
5 • Hybrid | Combine the above by site capability | Needs consistent contracts and ownership
Notes: Recommendation: Model 1 + Model 2 for the first end-to-end build; Model 3 for existing VMS integrations where accessible; selective Model 4 evidence capture, not blanket state recording. Model 5 is a design choice, not a bonus by name alone. Existing departmental recorders remain the primary full-video store.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 4
TEAM PROPOSAL
Make the claims technically precise
These changes strengthen the proposal and prevent avoidable questions.
GUJARAT CCTV / Proposed design • targets are not measured results
04
Correct the model descriptions
Existing recording remains in place; permissions, bandwidth and device load still need validation.
Historical playback may work through a local VMS API or recording interface.
Metadata correlation and vehicle history do not require a central VMS.
Correct the analytics claims
Edge processing relocates compute; it does not eliminate compute or operating cost.
Sightings establish observed locations. Any path between cameras is an inference.
AFIS / NAFIS use fingerprints; they are not direct video-to-identity databases.
Notes: Model 2 may use RTSP, ONVIF, vendor APIs or SDKs; it is not restricted to direct camera RTSP. Model 3 is an architectural federation layer, not inherently metadata-only: actual viewing and playback depend on each adapter and permissions. Registry health must distinguish reported status from tested live health. Facial identification and fingerprints must never be conflated. NAFIS is a fingerprint repository. No direct NAFIS access is assumed.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://www.onvif.org/profiles/profile-g/
https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080660
[/Sources]

## Slide 5
TEAM PROPOSAL
Scope the work in three layers
Complete the core chain before taking on additional analytics.
GUJARAT CCTV / Proposed design • targets are not measured results
05
BUILD FIRST
Registry + GIS
Feed onboarding and viewer
ANPR + watchlist matching
Alerts, history and evidence
ADD AFTER PASS
Outage recovery
Camera health and quality
One real VMS adapter
Measured bandwidth reduction
DEFER
Facial recognition
Unrestricted person search
Live national-database access
Full statewide video retention
Notes: Core includes role-based access, audit events and secure secrets from day one. Bonus scope is gated on passing the core demonstration, not a reason to omit baseline security. Facial recognition is outside this prototype and would require a separate authorised purpose, safeguards and evaluation. Vehicle appearance may help a human review a sighting but is not an identity proof.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 6
TEAM PROPOSAL
Keep video close to its source
Deployment target: departmental recording + regional analytics + central coordination.
GUJARAT CCTV / Proposed design • targets are not measured results
06
IP cameras / NVRs
Departmental VMS
Analog via DVR / encoder
Regional gateway: adapters • stream relay • ANPR • durable event queue
Central services: registry / GIS • watchlist • matching • alerts / audit
Video remains local by default. Metadata flows centrally; authorised viewing and incident clips are selective.
Notes: This is the proposed target topology. Each source connects through an authorised adapter. The regional gateway can consume either video or suitable source-generated analytics metadata. Local recorders continue recording independently. Regional workers publish standard sightings to central services; central matching avoids copying unrestricted watchlists to every camera. Where approved, a scoped and encrypted watchlist cache can enable offline regional alerts with expiry/version checks. The UI requests streams through the gateway and queries central APIs. Security, identity, camera permissions and monitoring span all layers. For the hackathon these logical services can be co-located on one host; do not claim physical edge savings if all feeds are pulled centrally.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 7
TEAM PROPOSAL
Adapt each site to what it supports
Discover capabilities first; never assume a camera or VMS implements every standard.
GUJARAT CCTV / Proposed design • targets are not measured results
07
Source condition | Preferred path | Fallback / constraint
VMS offers useful API | Adapter for streams, events and playback | Use permitted RTSP if API unavailable
IP camera / NVR | Approved stream + capability discovery | Check codec, sessions and reachability
Analog camera | DVR channel or video encoder output | No direct analog-to-IP software fix
Source has ANPR | Normalise vendor metadata; validate quality | Run our worker when quality is inadequate
Source inaccessible | Record blocker, owner and health state | No fabricated “connected” status
Notes: ONVIF profiles describe distinct feature sets: T advanced streaming, G recording/retrieval, M analytics metadata/events. Verify conformant device and client compatibility and supported optional functions. SDK licensing, session limits, network routes, read-only credentials and firmware vary by department. API wrappers must not be described as universal vendor support without actual tests. A simulator may test an adapter contract but is not evidence of real vendor integration.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://www.onvif.org/profiles/
https://www.onvif.org/profiles/profile-t/
https://www.onvif.org/profiles/profile-g/
https://www.onvif.org/profiles/profile-m/
[/Sources]

## Slide 8
TEAM PROPOSAL
Separate viewing from analytics
A video wall and continuous ANPR have different performance requirements.
GUJARAT CCTV / Proposed design • targets are not measured results
08
Viewing path
Use one source pull where possible; relay permitted streams to multiple clients.
Provide WebRTC viewing; retain an HLS fallback where appropriate.
Open selected tiles on demand; avoid decoding 50 full-resolution browser tiles.
Analytics path
Process all required accessible feeds continuously; report actual coverage.
Use calibrated sampling and plate-quality crops; do not sacrifice readable plates.
Store event timestamps, not browser display time; expose queue delay.
Notes: Candidate tools: MediaMTX plus FFmpeg or GStreamer for relay and decode. MediaMTX supports browser-facing protocols, but browser/codec compatibility may still require transcoding. Sample rate, resolution, camera angle and vehicle speed affect recall. Lowering inference FPS may not lower source bandwidth when the original stream still travels to the processing host. Regional placement, lower-bitrate source streams and on-demand central viewing drive real WAN savings. Ensure analytics continues when nobody has the dashboard open.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://mediamtx.org/docs/features/read
[/Sources]

## Slide 9
TEAM PROPOSAL
Make plate recognition reviewable
Use a pretrained baseline first; tune only after measuring errors on representative feeds.
GUJARAT CCTV / Proposed design • targets are not measured results
09
Recognition pipeline
Detect vehicle / plate → track within camera → select readable crops.
Recognise text on multiple frames; retain raw reads and the chosen plate.
Normalise spacing and case; preserve ambiguity and source evidence.
Validation discipline
Use varied day/night, angle, blur and plate-format samples.
Keep tuning and held-out footage separate; never split adjacent frames across both.
Measure missed passages and false alerts, not only OCR on handpicked crops.
Notes: ANPR means automatic number plate recognition. Candidate baseline: a licence-reviewed plate detector plus lightweight OCR such as PaddleOCR, evaluated on actual plate crops. Do not use a document VLM or LLM as the real-time default. Do not train a new detector from scratch in the hackathon unless baseline testing proves it essential. Plate syntax is a plausibility check, not evidence of identity. Include BH and other relevant formats; do not restrict recognition to GJ registrations. Avoid aggressive O/0 or I/1 substitutions. Pin model weights and code hashes, and review weight/data licences separately from toolkit licences.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://github.com/PaddlePaddle/PaddleOCR
[/Sources]

## Slide 10
TEAM PROPOSAL
Turn sightings into actionable alerts
A match is an investigative lead that requires evidence and human review.
GUJARAT CCTV / Proposed design • targets are not measured results
10
Stage | Proposed behaviour | What we retain
Read quality | Aggregate consistent reads within one passage | Raw reads, selected crop, confidence
Watchlist match | Exact normalised match to active authorised record | Record ID, purpose, version, expiry
Ambiguous read | Candidate for review; no automatic exact-match label | Alternatives and reason for uncertainty
Deduplication | One alert per watchlist item and camera passage | All underlying sightings remain searchable
Operator review | New → acknowledged → confirmed / rejected | Reviewer, time, reason and audit event
Notes: Confidence thresholds and the number of consistent frames are configurable hypotheses to calibrate on validation footage. Use fuzzy matches only in a separately labelled review queue; never silently rewrite OCR to the nearest watchlist entry. Exact OCR matching can still be wrong and does not establish the driver’s identity or wrongdoing. Do not suppress a new sighting at another camera when deduplicating. Record revoked/expired watchlist handling, source authority, and false-positive feedback. No automatic enforcement action.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 11
TEAM PROPOSAL
Show movement without overstating it
The GIS view should make evidence, uncertainty and missing coverage visible.
GUJARAT CCTV / Proposed design • targets are not measured results
11
Observed movement
Search plate + time window; order sightings by event time and camera.
Show camera coordinates, image evidence, timestamps and review status.
Retain duplicate reads internally; group them into a single camera passage.
Limits and safeguards
Label links between sightings as inferred movement, not verified road segments.
Flag clock drift, stale feeds, blind spots and conflicting sightings.
Do not treat an unreadable plate or absent sighting as proof of absence.
Notes: The brief asks for the complete route; explain that this can mean all observed sightings and a candidate path, but CCTV gaps cannot establish the actual traversed road. Ask the organisers how they evaluate route reconstruction. Preserve camera time, corrected UTC event time, ingestion time and clock-offset metadata. Display IST clearly for operators. Use realistic travel-time checks to flag implausible associations, not to fabricate a missing detection. Cloned plates and OCR errors can produce conflicting histories.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 12
TEAM PROPOSAL
Agree on the data contract early
A stable event envelope lets team members build independently.
GUJARAT CCTV / Proposed design • targets are not measured results
12
Record | Minimum content | Integrity / access rule
Camera | ID, department, GIS, source, capabilities, health | Secrets referenced, never embedded in export
Sighting | ID, camera, event time, raw / normalised plate | Confidence, model version, evidence reference
Watchlist | Record ID, plate, purpose, priority, validity | Authority, version, access scope and expiry
Alert | Sighting IDs, watchlist ID, match type, status | Unique dedup key; reviewer and audit trail
Evidence / audit | Clip or crop URI, hash, actor, action, time | Retention policy, export log, access checks
Notes: Proposed minimum schema, not an implementation claim. Add trace_id, schema_version, source_time, ingest_time and event_id to every event. Keep database constraints and idempotent consumers to prevent replay duplicates. Expose documented endpoints for camera onboarding, sightings, watchlists, alerts and evidence access. All reads and writes must enforce department and case scope server-side. Retention and legal hold must be explicit per record category. A hash detects byte changes but does not alone prove the original capture is authentic or legally admissible.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 13
TEAM PROPOSAL
Use a small, replaceable stack
Choose familiar components; avoid infrastructure work that delays the first real alert.
GUJARAT CCTV / Proposed design • targets are not measured results
13
Layer | Prototype candidate | Reason / guardrail
UI + GIS | React + Leaflet | Map, alert queue and searchable history
Application API | FastAPI; documented OpenAPI contracts | One modular service initially
Stream + ANPR | MediaMTX, FFmpeg; detector + OCR worker | Replaceable models; benchmark decode too
Data + delivery | PostgreSQL / PostGIS + durable outbox | Reliable events without Kafka on day one
Evidence + deploy | Local protected files; S3-compatible later; Compose | Pinned versions, secrets, backup and metrics
Notes: These are proposed choices, not requirements or verified benchmarks. A transactional outbox stores events durably in PostgreSQL and retries delivery; unique IDs make processing idempotent. A disk spool at a regional gateway is needed when that gateway cannot reach the central database. Add a broker only when measured load or distributed operations justifies it. Use built-in PostgreSQL indexes for the prototype; avoid Elasticsearch unless search benchmarks demand it. Kubernetes is a later operational choice, not proof of scalability. Lock dependency versions and scan model/dependency licences.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://mediamtx.org/docs/features/read
https://github.com/PaddlePaddle/PaddleOCR
[/Sources]

## Slide 14
TEAM PROPOSAL
Use representative watchlists now
Real government integration depends on official authorisation and technical access.
GUJARAT CCTV / Proposed design • targets are not measured results
14
Working prototype
Create synthetic vehicle watchlist records with validity, source and priority.
Run actual matching against detections; keep the backend operational.
Clearly label synthetic data and recorded footage in demonstrations.
Future integration boundary
Use approved adapters for VAHAN, SARATHI and eGujCop when granted access.
Treat AFIS / NAFIS as fingerprint-related systems, outside direct ANPR matching.
Do not scrape official portals or claim live integration from a mock endpoint.
Notes: The brief allows representative datasets, but explicitly rejects non-operational mockups. Use fabricated watchlist identities and authorised video: do not seed arbitrary real private vehicles as suspects. VAHAN/SARATHI/eGujCop integration is a proposed boundary; actual schemas, permissions, access channels and lawful purposes must be confirmed with the responsible departments. We do not assume any public API grants production access. No biometric identification or unrestricted person tracking is part of the initial scope.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080660
[/Sources]

## Slide 15
TEAM PROPOSAL
Build security into the first release
Limit access to authorised cameras, records and evidence for a defined purpose.
GUJARAT CCTV / Proposed design • targets are not measured results
15
Access and network controls
Separate operator, reviewer and administrator roles; enforce department scope.
Use TLS / approved private connectivity; keep camera credentials server-side.
Allowlist source destinations; block arbitrary URL fetching and public camera exposure.
Data and operational controls
Log searches, exports and watchlist changes; protect evidence and audit records.
Use authorised footage, minimise data, and set approved retention and deletion.
Require human verification; redact unnecessary faces and plates in shared demos.
Notes: These are proposed engineering safeguards, not a legal compliance opinion. Obtain department approval for purpose, access, retention, sharing and deployment before live use. Onboarding URLs can create SSRF risk: validate destinations and prohibit access to host metadata or unrelated internal services. Secrets must not appear in repositories, query logs, screenshot recordings or browser URLs. Add encrypted disks/backups, credential rotation, session expiry, rate limits and signed short-lived evidence links. An unlisted or anyone-with-link video is still shareable; only include material cleared for that release.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 16
TEAM PROPOSAL
Survive outages and bad inputs
Reliability features are valuable only when the team demonstrates the failure and recovery.
GUJARAT CCTV / Proposed design • targets are not measured results
16
Recover without losing control
Reconnect with bounded retries; show degraded or offline camera status.
Spool permitted events locally; replay with stable IDs after connectivity returns.
Expire stale cached watchlists and mark delayed alerts as delayed.
Prove the behaviour
Disconnect a feed, interrupt central connectivity, then restart a worker.
Check recovery time, queue growth, duplicate alerts and missing events.
Test revoked access, expired evidence and database restoration.
Notes: Prototype durability: an event accepted into the durable store should survive worker restart; show the limits explicitly. Frames or events created while a camera itself is unreachable may be unrecoverable unless source playback and permissions allow recovery. A buffer must be bounded by disk space, retention and backpressure policy. Source recording must continue independently. Production disaster recovery: redundant regional workers with dedup/fencing, central database failover, encrypted offsite backup and restore drills. Proposed RPO ≤5 min and RTO ≤30 min require validation and budget; do not claim zero loss or tested high availability from a single-host demo.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 17
TEAM PROPOSAL
Measure success before adding scope
Internal acceptance targets below are proposed; they are not official thresholds or results.
GUJARAT CCTV / Proposed design • targets are not measured results
17
Check | Proposed gate | Measurement
Feed coverage | All supplied accessible feeds onboarded | ~50-camera ledger; blockers and active count
Alert latency | p95 ≤5 seconds on nominated hardware | Readable frame time → stored/displayed alert
ANPR quality | ≥95% alert precision; ≥85% passage recall | Held-out events; readable subset + overall
Runtime stability | 60 minutes at required concurrency | Queue delay, frame drops, CPU/GPU and RAM
Recovery + audit | No duplicate alert after event replay | Outage test, permissions and export trace
Notes: Reset targets after baseline testing if feed quality makes them infeasible; report the reason rather than selecting only easy footage. Precision = correct watchlist alerts / all generated watchlist alerts. Passage recall = correctly alerted watchlisted passages / all labelled watchlisted passages. Report end-to-end recall over all passages and separately over those where a plate is independently readable. Sample recommendation: at least 200 labelled passages across available conditions including at least 30 controlled positive passages, when feasible; disclose counts and limitations. Avoid repeated frames as independent examples. Report confidence intervals and absolute false-alert counts. Also report exact plate accuracy, camera reachability, analytics-active count, p50/p95/max latency and capture-to-ingest delay.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 18
TEAM PROPOSAL
Plan capacity from measurements
Illustrative arithmetic only. 2 Mb/s per camera; decimal units; no overhead or replication.
GUJARAT CCTV / Proposed design • targets are not measured results
18
Load assumption | 50 cameras | 80,000 cameras
Continuous source video | 100 Mb/s | 160 Gb/s
Full video per day | 1.08 TB | 1.728 PB
15-day full video archive | 16.2 TB | 25.92 PB
Metadata: 0.2 events/s/camera 2 kB per event | 20 kB/s; 1.728 GB/day | 32 MB/s; 2.765 TB/day
Notes: Video rate = camera count × bitrate. Daily bytes = bits/s × 86,400 / 8. At 2 Mb/s each camera generates 21.6 GB/day. Metadata values assume 2,000 bytes per event excluding images: 80,000 × 0.2 × 2,000 = 32,000,000 bytes/s, approximately 256 Mb/s and 2.7648 TB/day. Metadata volume is traffic-dependent and not necessarily tiny at state scale. These are capacity scenarios, not measured feed statistics or advertised savings. Local full-video storage remains a cost under the hybrid model; we avoid duplicating all of it centrally. WAN reduction requires analytics before the constrained WAN link.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 19
TEAM PROPOSAL
Budget evidence and compute separately
Selective retention is cheaper than copying everything, but still needs explicit limits.
GUJARAT CCTV / Proposed design • targets are not measured results
19
Evidence and retention
Example: a 10-second clip at 2 Mb/s is approximately 2.5 MB.
100,000 clips/day → 250 GB/day; 30 days → 7.5 TB before replicas.
Prototype policy: hot metadata and incident crops; local full-video retention persists.
Compute sizing
Measure full pipeline throughput: decode, detection, OCR, matching and persistence.
Workers = ceiling(required frames/s ÷ safe measured frames/s per worker).
2 FPS is a hypothesis. Calibrate from dwell time and passage recall; do not promise one GPU.
Notes: Illustrative throughput scenario only: if a worker sustains 100 end-to-end FPS and safe utilisation is 70%, effective capacity is 70 FPS; 50 cameras at 2 FPS require ceiling(100/70)=2 workers. At 80,000 cameras at 2 FPS, the same assumptions imply 2,286 workers, showing why camera selection, existing source analytics and optimisation matter. Actual inference demand differs from decode demand, and high-speed plates may require higher sampling. Suggested target retention tiers for discussion: recent metadata 30 days hot; approved older metadata up to 90 days warm; incident evidence cold only for the approved case period/legal hold. These are planning assumptions, not legal retention rules. Delete expired data and purge caches/backups according to policy.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 20
TEAM PROPOSAL
Make cost assumptions auditable
Illustrative 14-day cost arithmetic, not the four-day build; replace rates with approved quotes.
GUJARAT CCTV / Proposed design • targets are not measured results
20
Item / assumption | Calculation | Illustrative amount
2 GPU workers; ₹100 / worker-hour | 2 × 24 × 14 × ₹100 | ₹67,200
Application / database allowance | Assumed fixed allowance | ₹10,000
Storage / monitoring allowance | Assumed fixed allowance | ₹5,000
Contingency | 20% of ₹82,200 | ₹16,440
Scenario total | Excludes staff, tax, network / egress | ₹98,640
Notes: This is a transparent budget scenario with deliberately hypothetical unit rates, not financial advice, an approved budget, a vendor quote or an estimate based on measured hardware needs. Using an already authorised server can reduce incremental rental cost; compute is not free and existing server access is unconfirmed. Do not rent for 14 days continuously if scheduled testing suffices. Statewide TCO must include camera remediation, vendor connector licences, regional compute, central services, network, evidence retention, replicas/DR, security, AMC and personnel. Formula: implementation + 12 × monthly operations for year one. Compare equivalent coverage, retention, availability and support against full central VMS. Do not claim a savings percentage before that comparison.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 21
TEAM PROPOSAL
Get the departmental facts on day one
Use one onboarding sheet per department, plus a camera-level capability ledger.
GUJARAT CCTV / Proposed design • targets are not measured results
21
Ask for | Minimum information | Why it matters
Ownership + approval | Department contact; permitted cameras and purpose | Authorised scope and escalation route
Feeds + devices | Camera IDs, coordinates, codec, FPS, bitrate, VMS | Integration path and stream budget
Network + credentials | Routes, firewall, VPN, read-only access, limits | Reachability without exposing devices
Video + time | Retention, playback API, timezone and clock drift | Evidence retrieval and correct ordering
Analytics + resources | Sample footage, plate quality, existing ANPR, GPU | Feasibility and baseline sizing
Notes: Also ask about firmware, vendor/model, channel mapping, stream session caps, maintenance/AMC constraints, camera orientation, day/night settings and consent/permissions for private cameras. Collect secret references through a secure channel, not plaintext spreadsheets. Confirm event rate, local uplink bandwidth, incident clip export rights and the database-integration authority. Clarify the official deadline, demo duration, on-site PoC requirements and allowed tools/deployment environments. No deadline or team size is given in the attached brief, so our following schedule is a planning scenario.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 22
TEAM PROPOSAL
A 4-day solo P0, code by Grok or Codex
One person. Sequence workstreams. Compress original Days 1-3 into the first two days.
GUJARAT CCTV / Proposed design • targets are not measured results
22
DAYS 1-2
Escalate government-feed access
Freeze event schema
Ledger all accessible cameras
First real sighting + alert + GIS
DAY 3
Expand analytics toward ~50
Calibrate sampling from dwell time
Watchlist + evidence + history
Disclose actual analytics coverage
DAY 4
Feature freeze at midday
Record both required demos
Finish HLD, report and links
No new features after midday
Notes: This plan is aggressive and conditional on permissions, working streams, usable baseline models and hardware. Day 1: source survey, deployment skeleton and schema. Day 2: first source → decode → OCR → DB event. Day 3: second integration path and one full watchlist alert. Days 4–5: camera onboarding and UI history. Days 6–8: quality, permissions and selective evidence. Days 9–10: held-out evaluation and concurrency. Day 11: recovery/security checks. Day 12: feature freeze. Day 13: videos/HLD/report. Day 14: rehearsal and access verification. Critical path is access → decode → OCR → stored sighting → alert → multi-feed proof. Documentation and security run throughout.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 23
TEAM PROPOSAL
Sequence four workstreams as one person
Grok/Codex generates each module. The human owns access, gates and demos.
GUJARAT CCTV / Proposed design • targets are not measured results
23
Stream | Model generates | Handoff / completion check
A • Integration + deployment | Feed adapters, relay, health, deployment | Stream/camera contract; all accessible cameras in ledger
B • ANPR + evaluation | Model baseline, crop selection, validation | Versioned sighting events + quality report
C • Backend + security | Registry, watchlist, matching, access, audit | Stable APIs; replay-safe alerts and permissions
D • UI + GIS + demo | Viewer, map, alert review, history, exports | Real backend journey; no hardcoded outputs
Notes: Role assignment should follow availability and familiarity, not job titles. Each owner has a named reviewer from another role. D can prototype against a documented local fixture while C implements APIs; replace fixtures in the actual demonstration. B can evaluate on authorised recorded inputs while A works on source integration. A and B jointly validate decode/inference performance. C and D jointly validate alert status transitions, evidence URLs and server-enforced access. Every day produce an integrated runnable build, not separate branches that only work individually.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 24
TEAM PROPOSAL
Some tasks need joint sign-off
One person owns delivery; another checks the integration or risk.
GUJARAT CCTV / Proposed design • targets are not measured results
24
Task | Working mode | Acceptance evidence
Schema + API contract | C owns; A/B/D review once | Sample event and endpoint contract frozen
Feed-to-alert integration | A + B + C; D validates display | Ledger of accessible cameras; actual plate and evidence
ANPR ground truth | B labels; independent teammate checks | Held-out set and disputed-label log
Security + recovery | A + C; D tests denied access | Restart/outage logs; cross-role access tests
Final demonstration | D presents; all rehearse | Both recordings, output report, working links
Notes: Do not put several people on the same file or vaguely assign “everyone” as owner. Use small branches and review pull requests; reserve shared schema changes for explicit coordination. Researching vendor capabilities, building an adapter, labelling footage, building a UI screen, writing HLD sections and implementing a worker are all individually executable. Cross-component integration, independent validation, threat review and rehearsal benefit from two or more people. A solo builder can execute them sequentially but should seek an independent reviewer when available.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 25
TEAM PROPOSAL
Solo 4-day build with Grok or Codex
Not 5-7 weeks. One person plus generated code; feed access is still the blocker.
GUJARAT CCTV / Proposed design • targets are not measured results
25
DAYS 1-2
Registry + own-feed
Persistent sighting
Exact watchlist alert
GIS inferred path
DAY 3
Ledger all ~50 cameras
Calibrate sampling
Disclose analytics coverage
Government-feed if decoded
DAY 4
Feature freeze midday
Record both demos
HLD, report, links
No new features after midday
Notes: A solo prototype is plausible; a complete statewide production platform is not a one-person hackathon deliverable. Use one modular backend, one UI, pre-trained models and Compose. Do not build a new VMS, broker platform or generic plugin marketplace. Keep the required feed coverage, government-feed demo and honest reports; cut optional analytics and extra vendor adapters first. If the actual deadline is two weeks, a solo builder needs substantial working reusable components or scope assistance. Adding people helps independent tasks but cannot eliminate feed-access dependencies. The schedule is not an assurance of delivery.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 26
TEAM PROPOSAL
Protect the critical path
If access or quality fails, expose the blocker early and use an honest fallback.
GUJARAT CCTV / Proposed design • targets are not measured results
26
Hard 4-day checkpoints
Midday D1: no government feed. Escalate access immediately.
End D1: no persistent sighting. Stop UI and infrastructure.
Midday D2: no end-to-end alert. Drop fuzzy, tracking, bonus.
Scope cuts
Midday D3: no stable concurrency. Lower sampling; disclose coverage.
After D4 midday: no new features.
Day-1 question is feed access, not model selection.
Notes: If a checkpoint fails, stop adding features and solve that dependency. If government feeds cannot be accessed, notify the organiser via the team’s authorised contact; do not imply the own-feed demo satisfies the government-feed test. If a VMS API is closed, use another permitted feed path and document the limitation. If clips cannot be exported, show local playback references and capture only permitted evidence; do not claim retained clips exist. If source images have no recoverable plate pixels, OCR cannot guarantee reconstruction. Display the error category and responsible dependency.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 27
TEAM PROPOSAL
Rehearse a 2–3 minute working demo
Suggested 150-second own-feed recording; the government-feed demonstration is a separate deliverable.
GUJARAT CCTV / Proposed design • targets are not measured results
27
Time | Show | Proof
0–20 s | Onboard source and display live / recorded feed | Camera ID, real backend and timestamp
20–45 s | Inspect the synthetic watchlist | Active target, source label and validity
45–85 s | Vehicle passage and automatic alert | Detected plate, crop, confidence and delay
85–115 s | Open GIS sightings and searchable history | Camera locations and observed timeline
115–150 s | Review alert, export report, show health | Audit trail and evidence references
Notes: Do not replace real backend behaviour with animations or pre-seeded alert rows. Recorded input is allowed in the brief, but label it clearly. Use the actual runtime and report relevant timing; disclose any edited waiting time in the video. For the government feed, show onboarding/viewing and available analytics with an output report of plates/vehicles and timestamps. Prepare a short fallback recording of an actual prior run for presentation resilience, but distinguish it from the live run and do not suggest it proves current connectivity. Redact credentials and obtain permission before including government footage in shareable links.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 28
TEAM PROPOSAL
Submit a consistent evidence package
The presentation supports the build; it does not replace any required working deliverable.
GUJARAT CCTV / Proposed design • targets are not measured results
28
Deliverable | Contents | Final check
Solution PPT / PDF | Model, justification, architecture and benefits | Claims match demonstrated behaviour
High-level design | Integration, security, sizing, deployment and DR | Assumptions, gaps and interfaces explicit
Own-feed + government demos | Working videos and required analytics output | Both included; sensitive data cleared
Output + test report | Plates, camera/time, evidence; quality and load | Reproducible run ID and configuration
Links + optional platform / code | Permitted viewer links; scoped test credentials | Access checked in clean browser
Notes: The brief requests own-feed screen recording maximum 2–3 minutes and a government-feed recording plus output report. It lists unlisted YouTube or Drive/OneDrive anyone-with-link viewer delivery. Check latest organiser instructions before release and share only cleared material. Hosted platform and repository links are additional options, not substitutes for required documents and videos. Use temporary, least-privilege test credentials via the approved submission route; no production credentials. Export reports should state source, event time, detection text, review status, model version and run configuration. No submission is performed by creating this planning deck.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 29
TEAM PROPOSAL
Scale only after the gates are passed
A roadmap toward 80,000 cameras is a deployment strategy, not a benchmark claim.
GUJARAT CCTV / Proposed design • targets are not measured results
29
50-FEED PILOT
Prove ~50-feed test
Survey several site types
Benchmark target hardware
Confirm approvals + support
DISTRICT → REGION
Deploy regional workers
Add verified VMS adapters
Measure WAN and quality
Test failover and restore
STATEWIDE WAVES
Partition cameras + events
Use capacity-based rollout
Audit access and retention
Track cost and service levels
Notes: Advance only when each wave meets agreed quality, load, availability, access and incident-response criteria. Scale event ingestion, stream relay, evidence storage and inference independently. Partition by region/camera/time; retain global query access under authorisation. Synthetic metadata load can validate event services but cannot prove 80,000-stream decode/inference performance. Test representative video concurrency and estimate capacity with measured throughput, then include redundancy and operator staffing. The statewide roadmap requires vendor contracts, hardware procurement, network planning and department cooperation.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 30
TEAM PROPOSAL
Start with one complete real alert
Solo kickoff: scope, Grok/Codex codegen, access and gates.
GUJARAT CCTV / Proposed design • targets are not measured results
30
Agree today
Approve the phased hybrid and vehicle-only prototype scope.
Lock the solo 4-day P0; Grok or Codex writes all application code.
Confirm deadline, feed access, compute availability and permitted data use.
Deliver first
Freeze the minimum event schema and camera onboarding sheet.
Put all accessible cameras in the ledger; report actual analytics coverage.
Publish a measured baseline before expanding features or making scale claims.
Notes: Our central argument is practical: use existing infrastructure, standardise the integration boundary, move video only when needed, and make every alert reviewable. The top-contender opportunity comes from a dependable demonstration and defensible evidence, not a long list of advanced analytics. The first concrete milestone is one full feed-to-alert workflow on real authorised inputs, followed by heterogeneous integration and required concurrency.
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
[/Sources]

## Slide 31
TEAM PROPOSAL
Source basis and planning limits
Requirements come from the supplied brief. Architecture, timelines and targets are recommendations.
GUJARAT CCTV / Proposed design • targets are not measured results
31
Source | Used for | Status
GUJARAT POLICE HACKATHON.md | Models, test case, deliverables and evaluation | User-provided requirements baseline
ONVIF • Profiles T / G / M | Streaming, recording and metadata distinctions | Official specifications overview
PIB / MHA • NAFIS | Fingerprint-system clarification | Official release, 4 December 2024
MediaMTX + PaddleOCR repositories | Candidate implementation components | Official project documentation
Team proposal / arithmetic | Schedule, acceptance gates and cost scenarios | Unmeasured; validate before commitment
Notes: Sources checked 31 August 2026. Full URLs are in the slide notes wherever used. No source establishes that the proposed prototype already works. No formal legal compliance assessment, live government-system connection, hardware benchmark, supplier quote or submission has been performed. Numerical costs are illustrative assumptions and capacity arithmetic excludes overhead where stated.
https://www.onvif.org/profiles/
https://www.onvif.org/profiles/profile-t/
https://www.onvif.org/profiles/profile-g/
https://www.onvif.org/profiles/profile-m/
https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080660
https://mediamtx.org/docs/features/read
https://github.com/PaddlePaddle/PaddleOCR
[Sources]
User-provided GUJARAT POLICE HACKATHON.md, Steps 1–7; supplied brief is the requirements baseline. No official deadline or numerical scoring weights supplied.
https://www.onvif.org/profiles/
https://www.onvif.org/profiles/profile-t/
https://www.onvif.org/profiles/profile-g/
https://www.onvif.org/profiles/profile-m/
https://www.pib.gov.in/PressReleasePage.aspx?PRID=2080660
https://mediamtx.org/docs/features/read
https://github.com/PaddlePaddle/PaddleOCR
[/Sources]